## ⚙️ Settings
⚙️ SYSTEM SETTINGS & LOOKUP TABLES — ARAB UNITY SCHOOL ¦ AY 2025-26
Status | Priority | Category | Location | Term | Assigned To | ⚙️ KPI Target | Value
⏳ Pending | 🔴 Critical | Electrical | Main Building | Term 1 | Maintenance Team | Completion Rate Target | 0.75
🔄 In Progress | 🟠 High | Plumbing | Block A – Boys | Term 2 | Cleaning Crew | Max Overdue Tasks | 5
⏸ On Hold | 🟡 Medium | Civil / Building | Block B – Girls | Term 3 | IT Team | Max Critical Pending | 2
✅ Completed | 🟢 Low | HVAC / AC | Primary Section | Summer | Electrical Team | Annual Budget Threshold AED | 500000
❌ Cancelled |  | Painting | Taher Hall |  | HVAC Contractor | On-Time Rate Target | 0.85
|  | Carpentry | Admin Office |  | Safety Officer
|  | Cleaning | Gym / Sports Hall |  | Pool Contractor
|  | IT / AV Equipment | Swimming Pool |  | External Vendor
|  | Safety & Security | Canteen / Kitchen |  | In-House
|  | Landscaping | Parking
|  | Furniture | Outdoor / Playground
|  | Pest Control | Library
|  | Other | Science Lab
Art Room
IT Lab
Auditorium
Toilets
Storage Room
Other

## 📋 Task Tracker
🏫 ARAB UNITY SCHOOL — MAINTENANCE MANAGEMENT SYSTEM ¦ AY 2025-26 (ANNUAL)
# | Task ID | Task Title | Category | Location | Term | Priority | Status | Assigned To | Reported By | Date Reported | Due Date | Date Completed | Days to Close | Overdue? | Cost (AED) | Vendor | % Progress | Health Score | Notes | 📎 Attachment / File Link
1 | MNT-001 | Fix broken ceiling tiles – Classroom B3 | Civil / Building | Block A – Boys | Term 1 | 🟠 High | ✅ Completed | Maintenance Team | Principal | 15/09/2025 | 25/09/2025 | 24/09/2025 |  | #VALUE! | 1200 | Al Noor Contractors | 100% | 100 | Completed on time
2 | MNT-002 | AC unit not cooling – Science Lab | HVAC / AC | Science Lab | Term 1 | 🔴 Critical | ✅ Completed | HVAC Contractor | Vice Principal | 20/09/2025 | 22/09/2025 | 22/09/2025 |  | #VALUE! | 800 | Cool Air Services | 100% | 100 | Emergency fix
3 | MNT-003 | Repaint exterior wall – Main entrance | Painting | Main Building | Term 1 | 🟡 Medium | ✅ Completed | External Vendor | Head of Operations | 01/10/2025 | 20/10/2025 | 18/10/2025 |  | #VALUE! | 3500 | BrightPaint LLC | 100% | 100 | Completed before inspection
4 | MNT-004 | Replace faulty electrical sockets – IT Lab | Electrical | IT Lab | Term 1 | 🟠 High | ✅ Completed | Electrical Team | Facility Officer | 05/10/2025 | 10/10/2025 | 09/10/2025 | 123 |  | 450 | Spark Electric Co. | 100% | 100 | 6 sockets replaced
5 | MNT-005 | Unclog drain – Boys toilets Block A | Plumbing | Toilets | Term 1 | 🔴 Critical | ✅ Completed | Maintenance Team | Principal | 12/10/2025 | 13/10/2025 | 13/10/2025 |  | #VALUE! | 200 | In-House | 100% | 100 | Same day fix
6 | MNT-006 | Install new projector – Auditorium | IT / AV Equipment | Auditorium | Term 1 | 🟡 Medium | ✅ Completed | IT Team | Vice Principal | 15/10/2025 | 30/10/2025 | 28/10/2025 |  | #VALUE! | 5800 | TechVision UAE | 100% | 100 | Installed & tested
7 | MNT-007 | Replace broken fence panel – Playground | Civil / Building | Outdoor / Playground | Term 1 | 🟠 High | ✅ Completed | External Vendor | Head of Operations | 20/10/2025 | 01/11/2025 | 30/10/2025 |  |  | 950 | SafeBuild Contractors | 100% | 100 | Safety hazard resolved
8 | MNT-008 | CCTV camera replacement – Block B | Safety & Security | Block B – Girls | Term 1 | 🟠 High | ✅ Completed | IT Team | Facility Officer | 25/10/2025 | 10/11/2025 | 08/11/2025 |  |  | 2100 | SecureVision Systems | 100% | 100 | 5 cameras replaced
9 | MNT-009 | Pest control – Canteen & Storage | Pest Control | Canteen / Kitchen | Term 1 | 🟡 Medium | ✅ Completed | External Vendor | Principal | 01/11/2025 | 05/11/2025 | 04/11/2025 | 90 |  | 600 | PestFree UAE | 100% | 100 | Monthly treatment
10 | MNT-010 | Repair water fountain – Main lobby | Plumbing | Main Building | Term 1 | 🟢 Low | ✅ Completed | Maintenance Team | Vice Principal | 10/11/2025 | 30/11/2025 | 25/11/2025 |  | #VALUE! | 300 | In-House | 100% | 100 | Spare part arrived late
11 | MNT-011 | Library roof leak – emergency patch | Civil / Building | Library | Term 1 | 🔴 Critical | ✅ Completed | External Vendor | Head of Operations | 15/11/2025 | 17/11/2025 | 17/11/2025 |  | #VALUE! | 1800 | Al Noor Contractors | 100% | 100 | Full repair planned T3
12 | MNT-012 | Generator annual service | Electrical | Main Building | Term 1 | 🟠 High | ✅ Completed | Electrical Team | Facility Officer | 20/11/2025 | 30/11/2025 | 28/11/2025 |  | #VALUE! | 2500 | Spark Electric Co. | 100% | 100 | Certificate obtained
13 | MNT-013 | Swimming pool pump replacement | Plumbing | Swimming Pool | Term 2 | 🟠 High | ✅ Completed | External Vendor | Principal | 05/01/2026 | 20/01/2026 | 18/01/2026 |  | #VALUE! | 3200 | PoolTech UAE | 100% | 100 | New pump installed
14 | MNT-014 | Fire alarm annual test & service | Safety & Security | Main Building | Term 2 | 🔴 Critical | ✅ Completed | Safety Officer | Facility Officer | 08/01/2026 | 15/01/2026 | 14/01/2026 |  | #VALUE! | 4500 | FireSafe Systems | 100% | 100 | Civil Defence cert. received
15 | MNT-015 | Taher Hall stage repaint | Painting | Taher Hall | Term 2 | 🟢 Low | ✅ Completed | Maintenance Team | Head of Operations | 15/01/2026 | 10/02/2026 | 08/02/2026 |  |  | 1100 | BrightPaint LLC | 100% | 100 | Before Annual Day
16 | MNT-016 | Gym floor varnishing | Carpentry | Gym / Sports Hall | Term 2 | 🟡 Medium | ✅ Completed | External Vendor | Vice Principal | 20/01/2026 | 15/02/2026 | 14/02/2026 |  | #VALUE! | 2800 | FloorPro UAE | 100% | 100 | 3-day drying, area closed
17 | MNT-017 | Primary door lock replacement | Carpentry | Primary Section | Term 2 | 🟠 High | ✅ Completed | Maintenance Team | Principal | 22/01/2026 | 30/01/2026 | 29/01/2026 |  | #VALUE! | 650 | In-House | 100% | 100 | All 8 locks replaced
18 | MNT-018 | Science lab fume hood repair | HVAC / AC | Science Lab | Term 2 | 🔴 Critical | ✅ Completed | HVAC Contractor | Vice Principal | 25/01/2026 | 05/02/2026 | 04/02/2026 |  |  | 1900 | Cool Air Services | 100% | 100 | H&S compliance
19 | MNT-019 | Parking lot LED lighting upgrade | Electrical | Parking | Term 2 | 🟡 Medium | ✅ Completed | Electrical Team | Facility Officer | 01/02/2026 | 20/02/2026 | 19/02/2026 |  | #VALUE! | 3600 | Spark Electric Co. | 100% | 100 | Energy saving upgrade
20 | MNT-020 | Canteen exhaust fan replacement | HVAC / AC | Canteen / Kitchen | Term 2 | 🟠 High | ✅ Completed | HVAC Contractor | Head of Operations | 05/02/2026 | 15/02/2026 | 14/02/2026 |  | #VALUE! | 750 | Cool Air Services | 100% | 100 | Old fan replaced
21 | MNT-021 | Fix broken ceiling tiles – Classroom B3 | Civil / Building | Block A – Boys | Term 3 | 🟠 High | 🔄 In Progress | Maintenance Team | Principal | 01/03/2026 | 10/03/2026 |  | 66 |  | 1200 | Al Noor Contractors | 40% | 60 | 3 tiles cracked
22 | MNT-022 | AC unit not cooling – Science Lab | HVAC / AC | Science Lab | Term 3 | 🔴 Critical | ⏳ Pending | HVAC Contractor | Vice Principal | 03/03/2026 | 05/03/2026 |  | 7 |  | 800 | Cool Air Services | 0% | 10 | Class relocated
23 | MNT-023 | Repaint exterior – Admin entrance | Painting | Admin Office | Term 3 | 🟡 Medium | ⏳ Pending | External Vendor | Head of Operations | 05/03/2026 | 25/03/2026 |  | -54 | #VALUE! | 3500 | BrightPaint LLC | 0% | 50 | Spring break scheduled
24 | MNT-024 | Replace faulty sockets – Block B | Electrical | Block B – Girls | Term 3 | 🟠 High | ⏸ On Hold | Electrical Team | Facility Officer | 07/03/2026 | 18/03/2026 |  | -115 | #VALUE! | 450 | Spark Electric Co. | 10% | 40 | Awaiting parts
25 | MNT-025 | CCTV camera replacement – Block C | Safety & Security | Block A – Boys | Term 3 | 🟠 High | 🔄 In Progress | IT Team | Facility Officer | 28/02/2026 | 14/03/2026 |  |  | #VALUE! | 2100 | SecureVision Systems | 60% | 60 | 3 of 5 installed
26 | MNT-026 | Pest control – Canteen | Pest Control | Canteen / Kitchen | Term 3 | 🟡 Medium | ⏳ Pending | External Vendor | Principal | 05/03/2026 | 08/03/2026 |  | -54 |  | 600 | PestFree UAE | 0% | 50 | Monthly treatment
27 | MNT-027 | Library full roof repair | Civil / Building | Library | Term 3 | 🔴 Critical | ⏳ Pending | External Vendor | Head of Operations | 06/03/2026 | 30/03/2026 |  | -85 | #VALUE! | 8500 | Al Noor Contractors | 0% | 10 | Permanent fix for T1 patch
28 | MNT-028 | Gym wall painting | Painting | Gym / Sports Hall | Term 3 | 🟢 Low | ⏳ Pending | External Vendor | Vice Principal | 08/03/2026 | 30/03/2026 |  | -146 | #VALUE! | 1800 | BrightPaint LLC | 0% | 50
29 | MNT-029 | IT lab server room AC | HVAC / AC | IT Lab | Term 3 | 🔴 Critical | 🔄 In Progress | HVAC Contractor | Facility Officer | 02/03/2026 | 09/03/2026 |  | 35 |  | 1900 | Cool Air Services | 50% | 60 | Server overheating risk
30 | MNT-030 | Outdoor lighting – playground | Electrical | Outdoor / Playground | Term 3 | 🟡 Medium | ⏳ Pending | Electrical Team | Principal | 09/03/2026 | 20/03/2026 |  | -177 | #VALUE! | 2200 | Spark Electric Co. | 0% | 50 | Safety upgrade
31 | MNT-031
32 | MNT-032
33 | MNT-033
34 | MNT-034
35 | MNT-035
36 | MNT-036
37 | MNT-037
38 | MNT-038
39 | MNT-039
40 | MNT-040
41 | MNT-041
42 | MNT-042
43 | MNT-043
44 | MNT-044
45 | MNT-045
46 | MNT-046
47 | MNT-047
48 | MNT-048
49 | MNT-049
50 | MNT-050
51 | MNT-051
52 | MNT-052
53 | MNT-053
54 | MNT-054
55 | MNT-055
56 | MNT-056
57 | MNT-057
58 | MNT-058
59 | MNT-059
60 | MNT-060
61 | MNT-061
62 | MNT-062
63 | MNT-063
64 | MNT-064
65 | MNT-065
66 | MNT-066
67 | MNT-067
68 | MNT-068
69 | MNT-069
70 | MNT-070
71 | MNT-071
72 | MNT-072
73 | MNT-073
74 | MNT-074
75 | MNT-075
76 | MNT-076
77 | MNT-077
78 | MNT-078
79 | MNT-079
80 | MNT-080
81 | MNT-081
82 | MNT-082
83 | MNT-083
84 | MNT-084
85 | MNT-085
86 | MNT-086
87 | MNT-087
88 | MNT-088
89 | MNT-089
90 | MNT-090
91 | MNT-091
92 | MNT-092
93 | MNT-093
94 | MNT-094
95 | MNT-095
96 | MNT-096
97 | MNT-097
98 | MNT-098
99 | MNT-099
100 | MNT-100
101 | MNT-101
102 | MNT-102
103 | MNT-103
104 | MNT-104
105 | MNT-105
106 | MNT-106
107 | MNT-107
108 | MNT-108
109 | MNT-109
110 | MNT-110
111 | MNT-111
112 | MNT-112
113 | MNT-113
114 | MNT-114
115 | MNT-115
116 | MNT-116
117 | MNT-117
118 | MNT-118
119 | MNT-119
120 | MNT-120
121 | MNT-121
122 | MNT-122
123 | MNT-123
124 | MNT-124
125 | MNT-125
126 | MNT-126
127 | MNT-127
128 | MNT-128
129 | MNT-129
130 | MNT-130
131 | MNT-131
132 | MNT-132
133 | MNT-133
134 | MNT-134
135 | MNT-135
136 | MNT-136
137 | MNT-137
138 | MNT-138
139 | MNT-139
140 | MNT-140
141 | MNT-141
142 | MNT-142
143 | MNT-143
144 | MNT-144
145 | MNT-145
146 | MNT-146
147 | MNT-147
148 | MNT-148
149 | MNT-149
150 | MNT-150
151 | MNT-151
152 | MNT-152
153 | MNT-153
154 | MNT-154
155 | MNT-155
156 | MNT-156
157 | MNT-157
158 | MNT-158
159 | MNT-159
160 | MNT-160
161 | MNT-161
162 | MNT-162
163 | MNT-163
164 | MNT-164
165 | MNT-165
166 | MNT-166
167 | MNT-167
168 | MNT-168
169 | MNT-169
170 | MNT-170
171 | MNT-171
172 | MNT-172
173 | MNT-173
174 | MNT-174
175 | MNT-175
176 | MNT-176
177 | MNT-177
178 | MNT-178
179 | MNT-179
180 | MNT-180
181 | MNT-181
182 | MNT-182
183 | MNT-183
184 | MNT-184
185 | MNT-185
186 | MNT-186
187 | MNT-187
188 | MNT-188
189 | MNT-189
190 | MNT-190
191 | MNT-191
192 | MNT-192
193 | MNT-193
194 | MNT-194
195 | MNT-195
196 | MNT-196
197 | MNT-197
198 | MNT-198
199 | MNT-199
200 | MNT-200
💰 ANNUAL TOTAL COST (All Tasks • AY 2025-26) | [14 empty] | 61750
Formulas:
Days to Close = IF([Date Completed]<>"",IF(AND(ISNUMBER(DATEVALUE([Date Completed])),ISNUMBER(DATEVALUE([Date Reported]))),DATEVALUE([Date Completed])-DATEVALUE([Date Reported]),""),IF(ISNUMBER(DATEVALUE([Date Reported])),TODAY()-DATEVALUE([Date Reported]),""))
Overdue? = IF(AND([Status]<>"✅ Completed",[Status]<>"❌ Cancelled",ISNUMBER(DATEVALUE([Due Date])),TODAY()>DATEVALUE([Due Date])),"🚨 OVERDUE","")

## 📊 Analytics Dashboard
📊 ANNUAL ANALYTICS DASHBOARD — ARAB UNITY SCHOOL ¦ AY 2025-26
⚡ ANNUAL KEY PERFORMANCE INDICATORS — AY 2025-26
📋 Total Tasks (Annual) | ✅ Completed |  | 🔄 In Progress |  | ⏳ Pending |  | 🚨 Overdue | ⏸ On Hold | 🔴 Critical Pending
-140 | 20 |  | 3 |  | 6 |  | 0 | 1 | 2
📌 Task Status Breakdown | [6 empty] | ⚡ Priority Distribution
⏳ Pending |  |  | 6 |  |  |  | 🔴 Critical |  | 8
🔄 In Progress |  |  | 3 |  |  |  | 🟠 High |  | 11
⏸ On Hold |  |  | 1 |  |  |  | 🟡 Medium |  | 8
✅ Completed |  |  | 20 |  |  |  | 🟢 Low |  | 3
❌ Cancelled |  |  | 0
📅 Term-by-Term Breakdown (Annual View)
Term | Total Tasks |  | Completed |  | In Progress |  | Pending | Total Cost (AED) | Completion %
🟣 Term 1 | 12 |  | 12 |  | 0 |  | 0 | 20200 | 100%
🔵 Term 2 | 8 |  | 8 |  | 0 |  | 0 | 18500 | 100%
🟡 Term 3 | 10 |  | 0 |  | 3 |  | 6 | 23050 | 0%
🟢 Summer | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
📈 Annual Performance Metrics | [6 empty] | 💰 Annual Cost Analytics
Annual Completion Rate |  | 66.67% |  | Target: 75% |  |  | Annual Total Cost |  | 61750
Annual On-Time Rate |  | 100% |  | Target: 85% |  |  | Completed Tasks Cost |  | 38700
Avg. Health Score |  | 81.3333 |  | / 100 |  |  | Pending + In Progress |  | 22600
Avg. Days to Close |  | 106.5 |  | days avg. |  |  | On-Hold Cost |  | 450
Annual Overdue Rate |  | 0% |  | Target: <10% |  |  | Critical Tasks Total |  | 20400
🗂️ Annual Analysis by Category
Category | Total | Completed | Pending | In Progress | On Hold | Total Cost
Electrical | 5 | 3 | 1 | 0 | 1 | 9200
Plumbing | 3 | 3 | 0 | 0 | 0 | 3700
Civil / Building | 5 | 3 | 1 | 1 | 0 | 13650
HVAC / AC | 5 | 3 | 1 | 1 | 0 | 6150
Painting | 4 | 2 | 2 | 0 | 0 | 9900
Carpentry | 2 | 2 | 0 | 0 | 0 | 3450
Cleaning | 0 | 0 | 0 | 0 | 0 | 0
IT / AV Equipment | 1 | 1 | 0 | 0 | 0 | 5800
Safety & Security | 3 | 2 | 0 | 1 | 0 | 8700
Landscaping | 0 | 0 | 0 | 0 | 0 | 0
Furniture | 0 | 0 | 0 | 0 | 0 | 0
Pest Control | 2 | 1 | 1 | 0 | 0 | 1200
Other | 0 | 0 | 0 | 0 | 0 | 0
🤖 Smart Alerts & System Recommendations (Auto-Updated)
✅ No overdue tasks. All deadlines met.
⚠️ CRITICAL: 2 Critical-priority tasks still Pending — do not delay.
✅ Workload is manageable.
✅ On-Hold count is acceptable.

## 🏢 Vendors
🏢 APPROVED VENDORS & CONTRACTORS — ARAB UNITY SCHOOL ¦ AY 2025-26
# | Vendor Name | Specialty | Contact Name | Phone | Email | Contract Expires | Rating | Notes
1 | Al Noor Contractors | Civil/Building | Mohammed Al Noor | +971 50 123 4567 | info@alnoor.ae | 31/12/2026 | ⭐⭐⭐⭐ | Preferred civil works
2 | Cool Air Services | HVAC/AC | Rajesh Kumar | +971 55 234 5678 | service@coolair.ae | 30/06/2026 | ⭐⭐⭐⭐⭐ | Priority HVAC vendor
3 | Spark Electric Co. | Electrical | Ali Hassan | +971 52 345 6789 | ali@sparkco.ae | 31/12/2026 | ⭐⭐⭐⭐ | Approved for all electrical
4 | BrightPaint LLC | Painting | James Wilson | +971 56 456 7890 | james@brightpaint.ae | 31/08/2026 | ⭐⭐⭐ | Scheduled works only
5 | TechVision UAE | IT/AV Equipment | Sara Al Mansoori | +971 50 567 8901 | sara@techvision.ae | 30/09/2026 | ⭐⭐⭐⭐⭐ | IT procurement partner
6 | SafeBuild Contractors | Civil/Building | Khalid Ibrahim | +971 54 678 9012 | khalid@safebuild.ae | 28/02/2027 | ⭐⭐⭐⭐ | Outdoor & structural
7 | SecureVision Systems | Safety & Security | Omar Al Rashid | +971 55 789 0123 | omar@securevision.ae | 31/07/2026 | ⭐⭐⭐⭐ | CCTV & access control
8 | PestFree UAE | Pest Control | Ramesh Patel | +971 52 890 1234 | info@pestfree.ae | 31/03/2027 | ⭐⭐⭐ | Monthly treatment
9 | In-House Maintenance | General | Maintenance Team | Ext. 101 | maintenance@aus.ae | N/A | ⭐⭐⭐⭐⭐ | All routine tasks
10 | PoolTech UAE | Plumbing | Hassan Al Ameri | +971 56 901 2345 | info@pooltech.ae | 30/06/2026 | ⭐⭐⭐⭐ | Pool & plumbing specialist
11 | FloorPro UAE | Carpentry | Robert Nair | +971 52 012 3456 | info@floorpro.ae | 31/12/2026 | ⭐⭐⭐ | Flooring specialist
12 | FireSafe Systems | Safety & Security | Ahmed Karimi | +971 55 123 4567 | service@firesafe.ae | 31/03/2026 | ⭐⭐⭐⭐⭐ | Fire safety compliance
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32

## 📅 Annual Schedule
📅 ANNUAL PREVENTIVE MAINTENANCE SCHEDULE — AY 2025-26
|  |  | 🟣 Term 1 (Sep–Dec) |  |  |  | 🔵 Term 2 (Jan–Mar) |  |  | 🟡 Term 3 (Apr–Jun) |  |  | 🟢 Summer (Jul–Aug)
# | Recurring Task / Activity | Responsible Team | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
1 | Weekly building inspection | Maintenance Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
2 | Toilets deep cleaning | Cleaning Crew | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
3 | Fire extinguisher inspection | Safety Officer | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
4 | Generator test run | Electrical Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
5 | AC filter cleaning – all units | HVAC Contractor | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
6 | CCTV system check | IT Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
7 | Playground equipment inspection | Maintenance Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
8 | Pool water treatment & testing | Pool Contractor | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
9 | Pest control – canteen & kitchen | PestFree UAE | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
10 | Corridor lighting check | Electrical Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
11 | Library AC maintenance | Cool Air Services | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
12 | Roof & drainage inspection | Al Noor Contractors | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
13 | Sports hall floor check | Maintenance Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
14 | Canteen deep clean & inspection | Cleaning Crew | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
15 | Emergency lighting test | Electrical Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
16 | Water tanks cleaning | Maintenance Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
17 | Annual fire drill | Safety Officer | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
18 | Garden & landscaping maintenance | Landscaping Team | bar: 🟣 Term 1 (Sep–Dec) Sep to 🟢 Summer (Jul–Aug) Aug
📊 Monthly Completion Summary (✅ Done count): |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 📈 Annual Trend Log
📈 ANNUAL KPI TREND LOG — ARAB UNITY SCHOOL ¦ AY 2025-26
Month | Term | Total Tasks | Completed | Pending | In Progress | Overdue | Completion % | On-Time % | Avg Health | Cost (AED) | Budget Var. | Tasks w/ Files | Notes
September | Term 1 | 45 | 32 | 6 | 5 | 2 | 71.1% | 88% | 72 | 38500 |  | 8 | Strong start
October | Term 1 | 38 | 28 | 5 | 3 | 1 | 73.7% | 90% | 75 | 29200 |  | 5
November | Term 1 | 52 | 40 | 7 | 4 | 3 | 76.9% | 85% | 78 | 44100 |  | 12 | Increased civil works
December | Term 1 | 29 | 25 | 2 | 2 | 0 | 86.2% | 93% | 85 | 21800 |  | 4 | Holiday — fewer tasks
January | Term 2 | 41 | 30 | 6 | 4 | 2 | 73.2% | 87% | 74 | 33700 |  | 7
February | Term 2 | 48 | 35 | 8 | 4 | 3 | 72.9% | 84% | 73 | 42500 |  | 9
March | Term 3 | [11 empty] | Current month
April | Term 3
May | Term 3
June | Term 3
July | Summer
August | Summer
📊 ANNUAL TOTALS |  | 253 | 190 | [6 empty] | 209800

## ℹ️ Guide
ℹ️ HOW TO USE — AUS MAINTENANCE SYSTEM ¦ AY 2025-26 (ANNUAL)
📋 Task Tracker (Annual)
Central database for ALL maintenance tasks across the full academic year. ▸ Column F = Term (Term 1 / Term 2 / Term 3 / Summer) — colour-coded automatically ▸ Column N = Days to Close — auto-calculated from date reported to completion ▸ Column O = Overdue? — auto-flags 🚨 OVERDUE when due date passes ▸ Column S = Health Score (0–100) — auto-rated by status & priority ▸ Annual cost total is at the bottom of column P ▸ Row turns GREEN when Completed ¦ RED tint for Critical tasks ▸ Supports up to 200 tasks for the full year
📎 File Attachment Column (Column U)
Column U — '📎 Attachment / File Link' is for linking supporting documents: HOW TO ATTACH A FILE: Option 1 — Paste the file path: • Right-click the cell → insert a hyperlink • Or type the full file path: C:\Maintenance\Photos\MNT-001.jpg • Or a SharePoint / Teams URL: https://ausschool.sharepoint.com/... Option 2 — Insert Hyperlink (recommended): 1. Click the cell in column U 2. Press Ctrl + K 3. Choose 'Existing File or Web Page' 4. Browse to your photo, PDF, or document 5. Click OK — cell shows clickable link Supported file types: Photos (.jpg/.png), PDFs, Word docs, invoices, certificates Tip: Store files in a shared folder (SharePoint / Teams) so all team members can open links
📊 Analytics Dashboard (Annual)
Full annual live analytics — auto-updates from Task Tracker. ▸ 7 Annual KPI cards ▸ Term-by-Term Breakdown: performance for each of 3 terms + summer ▸ Annual completion rate, on-time rate, avg health score, avg days to close ▸ Annual cost breakdown: total / completed / pending / critical ▸ Category & Location analysis ▸ 🤖 6 Smart Alerts — auto-flag issues as you work
📅 Annual Schedule
Preventive maintenance calendar across all 12 months. ▸ Colour-coded by Term: 🟣 T1 (Sep–Dec) ¦ 🔵 T2 (Jan–Mar) ¦ 🟡 T3 (Apr–Jun) ¦ 🟢 Summer ▸ ⏳ = Planned month for that task ▸ Click any ⏳ cell → dropdown: ✅ Done / 🔄 In Progress / ❌ Skip / ➡️ Rescheduled ▸ Summary row at the bottom counts completed tasks per month
📈 Annual Trend Log
Month-by-month KPI history for the full academic year. ▸ Fill in each month at month-end review ▸ Column M = Tasks with Attachments (count tasks that have files linked) ▸ Annual totals row auto-sums at the bottom ▸ Completion % column has green/red colour coding ▸ Use for DSIB evidence, board reports, annual review
⚙️ Settings
Lookup tables powering all dropdown menus. ▸ Edit any list item here → all dropdowns update everywhere ▸ KPI Targets (column N): adjust to your school's goals ▸ Annual Budget Threshold: set in row 7 of column N
💡 Tips & Best Practices
▸ Save after every session — share via SharePoint or Teams ▸ Use Ctrl+F to search any task or vendor ▸ Sort Task Tracker by Due Date or Priority for daily planning ▸ Add file links (Ctrl+K) immediately after task is logged ▸ Update Trend Log at the end of each month ▸ Print Analytics Dashboard (landscape A3) for management meetings ▸ Archive completed tasks at end of each term to keep tracker clean